## Sheet1
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
Product Backlog ID
Product Backlog ID | PECUNIABANK_01 | 1 | Test case Template | 2020-08-03 | 1.5 hrs |  | Completed
Product Backlog ID |  | 2 | Product Backlog | 2020-08-03 | 1 hr |  | Completed
Product Backlog ID |  | 3 | Sprint Plan Sheet | 2020-08-03 | 1 hr |  | Completed
Product Backlog ID |  | 4 | Entity Class Design | 2020-08-04 | 2 hrs |  | Completed
Product Backlog ID |  | 5 | Use Case Diagram | 2020-08-04 | 1.5 hrs |  | Completed
Product Backlog ID |  | 6 | Sequence Diagram | 2020-08-04 | 1.5 hrs |  | Completed
Product Backlog ID | PECUNIABANK_02 | 1 | Creating a Spring boot starter project | 2020-08-05 | .5hr | .5hr | Completed
Product Backlog ID |  | 2 | Adding dependencies in Pom.xml and initializing it | 2020-08-05 | 1 hr | 1hr | Completed
|  | 3 | Adding server, jpa and logging properties in application.properties | 2020-08-06 | 1 hr | 1hrs | Completed
3 | PECUNIABANK_03 | 1 | CREDIT TRANSACTIONS; DAO | 2020-08-07 | 3 hrs | 0.5 hrs | Completed
|  | 2 | CREDIT TRANSACTIONS; SERVICE | 2020-08-07 | 3 hrs | 0,5 hrs | Completed
|  | 3 | CREDIT TRANSACTIONS; CONTROLLER | 2028-08-08 | 3 hrs | 0,5 hrs | Completed
4 | PECUNIABANK_04 | 1 | Populating the test data in database | 2020-08-09 | 3 hr | 0.5 hrs | Completed
5 | PECUNIABANK_05 | 1 | Testing the functionalites in postman | 2020-08-10 | 2 hrs | 1hr | Completed