## ProductBacklog
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Type
This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog Product Backlog ID | This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.). Source | Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have Priority (M/S/C/W) | Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW. User Story ID | Brief description of the requirements necessary to fulfill the objective User Story Name | Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party. User | Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party. Scrum Team Assigned | Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex Complexity | Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low). Risk/ Impact | Defines whether the User Story is Functional, Non-Functional or Technical type. Type | This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied. User Acceptance Test Case ID | fdasf fdaf
1 | Standard document | High | PECUNIABANK:001 | Design Documentation for Backend application | Ganesh | Ganesh | Average | Low | Non-Functional | Design is fullfilled agaist Business requirement
2 | Standard document | High | PECUNIABANK:002 | Bootstraping the project | Ganesh | Ganesh | Low |  | Non-Functional | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | Standard document |  | PECUNIABANK:003 | Account | Ganesh | Ganesh |  | High | Functional | Designing the user cases against Business requirement
4 | Standard document | High | PECUNIABANK:004 | Transaction | Ganesh | Ganesh | Complex | Low | Functional | Designing the user cases against Business requirement
5 | Standard document | High | PECUNIABANK:005 | Loan | Ganesh | Ganesh | Complex | High | Functional | Designing the user cases against Business requirement
6 | Standard document | High | PECUNIABANK:006 | Passbook | Ganesh | Ganesh | Complex | High | Functional | Designing the user cases against Business requirement
| Work session | High | PECUNIABANK:007 | Populating test data in database | Ganesh | Ganesh | Simple |  | Non-Functional
7 | Work session | High | PECUNIABANK:008 | Testing all the functionalities in postman whether all are working or not | Ganesh | Ganesh | Complex | High | Non-Functional
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41

## Rakesh
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimated Time | Adjustment Estimate | Status
1 | PECUNIA_BANK:001 | 1 | Test Cases Template |  | 2020-08-03 | 1 hr | 2 hrs | Completed
|  | 2 | Product Backlog Sheet |  | 2020-08-03 | 1 hr | 1.5 hrs | Completed
|  | 3 | Sprint plan sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | Completed
|  | 4 | Entity Class Diagram |  | 2020-08-04 | 1.5 hrs | 1.5 hrs | Completed
|  | 5 | Use Case Diagram |  | 2020-08-04 | 1 hr | 1.5 hrs | Completed
|  | 6 | Sequence Diagram |  | 2020-08-04 | 1 hr | 1 hr | Completed
2 | PECUNIA_BANK:002 | 1 | Creating a Spring boot starter project |  | 2020-08-05 | 0.5 hr | 0.5 hr | Completed
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 2020-08-05 | 0.25 hr | 0.5 hr | Completed
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 2020-08-05 | 0.5 hr | 0.5 hr | Completed
3 | PECUNIA_BANK:003 | 1 | ADD ACCOUNT | DAO LAYER | 2020-08-06 | 3 hrs | 2 hrs | Completed
|  |  |  | SERVICE LAYER | 2020-08-07 | 3 hrs | 2 hrs | Completed
|  |  |  | ENTITY LAYER | 2020-08-06 | 3 hrs | 1.5 hrs | Completed
|  |  |  | SERVICE IMPLEMENTATION LAYER | 2020-08-08 | 3 hrs | 2.5 hrs | Completed
|  | 2 | UPDATE ACCOUNT | DAO LAYER | 2020-08-06 | 3 hrs | 2 hrs | Completed
|  |  |  | SERVICE LAYER | 2020-08-07 | 3 hrs | 2 hrs | Completed
|  |  |  | SERVICE IMPLEMENTATION LAYER | 2020-08-08 | 3 hrs | 1.5 hrs | Completed
|  | 3 | DELETE ACCOUNT | DAO LAYER | 2020-08-06 | 3 hrs | 1.5 hrs | Completed
|  |  |  | SERVICE LAYER | 2020-08-07 | 2 hrs | 1.5 hrs | Completed
|  |  |  | SERVICE IMPLEMENTATION LAYER | 2020-08-08 | 2 hrs | 1.5 hrs | Completed
4 | PECUNIA_BANK:007 | 13 | Populating the data in database |  | 2020-08-10 | 1.5 hrs | 2 hrs | Completed
5 | PECUNIA_BANK:008 | 14 | Testing all the functionalities in postman |  | 2020-08-10 | 2 hrs | 1 hr | Completed

## Lova Raju
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
Product Backlog ID
Product Backlog ID | PECUNIABANK_01 | 1 | Test case Template | 2020-08-03 | 1.5 hrs | .5 hr | Completed
Product Backlog ID |  | 2 | Product Backlog | 2020-08-03 | 1 hr | .5hr | Completed
Product Backlog ID |  | 3 | Sprint Plan Sheet | 2020-08-03 | 1 hr |  | Completed
Product Backlog ID |  | 4 | Entity Class Design | 2020-08-04 | 2 hrs | .5hr | Completed
Product Backlog ID |  | 5 | Use Case Diagram | 2020-08-04 | 1.5 hrs | 1 hr | Completed
Product Backlog ID |  | 6 | Sequence Diagram | 2020-08-04 | 1.5 hrs |  | Completed
Product Backlog ID | PECUNIABANK_02 | 1 | Creating a Spring boot starter project | 2020-08-05 | .5hr | .5hr | Completed
Product Backlog ID |  | 2 | Adding dependencies in Pom.xml and initializing it | 2020-08-05 | 1 hr | 1hr | Completed
|  | 3 | Adding server, jpa and logging properties in application.properties | 2020-08-06 | 1 hr | 1hrs | Completed
3 | PECUNIABANK_03 | 1 | DEBIT TRANSACTIONS; DAO | 2020-08-07 | 3 hrs | 0.5 hrs | Completed
|  | 2 | DEBIT TRANSACTIONS; SERVICE | 2020-08-07 | 3 hrs | 0,5 hrs | Completed
|  | 3 | DEBIT TRANSACTIONS; CONTROLLER | 2028-08-08 | 3 hrs | 0,5 hrs | Completed
4 | PECUNIABANK_04 | 1 | Populating the test data in database | 2020-08-09 | 3 hr | 0.5 hrs | Completed
5 | PECUNIABANK_05 | 1 | Testing the functionalites in postman | 2020-08-10 | 2 hrs | 1hr | Completed

## Venkata Sai
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK:001 | 1 | Test Cases Template |  | 2020-08-03 | 2 hrs | 1 hrs | completed
|  | 2 | Product Backlog Sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | completed
|  | 3 | Sprint plan sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | completed
|  | 4 | Entity Class Diagram |  | 2020-08-04 | 2 hrs |  | completed
|  | 5 | Use Case Diagram |  | 2020-08-04 | 2 hrs |  | completed
|  | 6 | Sequence Diagram |  | 2020-08-04 | 2 hrs |  | completed
2 | PECUNIABANK:002 | 1 | Creating a Spring boot starter project |  | 2020-08-05 | 1hrs | 0.5 hrs | completed
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 2020-08-05 | 1 hrs | 0.5 hrs | completed
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 2020-08-05 | 1 hrs | 0.5 hrs | completed
3 | PECUNIABANK:005 | 1 | PassBook Update | DAO | 2020-08-06 | 3 hrs | 1.5 hrs | completed
|  |  |  | SERVICE | 2020-08-07 | 3 hrs | 1.5 hrs | completed
|  |  |  | CONTROLLER | 2020-08-10 | 3 hrs | 1.5 hrs | completed
|  | 2 | Account Summary | DAO | 2020-08-10 | 3 hrs | 1.5 hrs | completed
|  |  |  | SERVICE | 2020-08-07 | 3 hrs | 1.5 hrs | completed
|  |  |  | CONTROLLER | 2020-08-05 | 3 hrs | 1.5 hrs | completed
4 | PECUNIABANK:007 | 1 | Populating the test data in database |  | 2020-08-05 | 3 hrs | 1hr | completed
5 | PECUNIABANK:008 | 1 | Testing the functionalites in postman | DAO,SERVICE,CONTROLLER | 2020-08-11 | 2 hrs

## Satyam
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK_01 | 1 | Test case Template | 2020-08-04 | 1.5 hrs |  | Completed
|  | 2 | Product Backlog | 2020-08-04 | 1 hr |  | Completed
|  | 3 | Sprint Plan Sheet | 2020-08-04 | 1 hr
|  | 4 | Entity Class Design |  | 2 hrs
|  | 5 | Use Case Diagram |  | 1.5 hrs
|  | 6 | Sequence Diagram |  | 1.5 hrs
2 | PECUNIABANK_02 | 1 | Creating a Spring boot starter project |  | .5hr | .5hr
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 1 hr | 1hr
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 1 hr | 1hrs
3 | PECUNIABANK_03 | 1 | DEBIT TRANSACTIONS; DAO |  | 3 hrs | 0.5 hrs
|  | 2 | DEBIT TRANSACTIONS; SERVICE |  | 3 hrs | 0,5 hrs
|  | 3 | DEBIT TRANSACTIONS; CONTROLLER |  | 3 hrs | 0,5 hrs
4 | PECUNIABANK_04 | 1 | Populating the test data in database |  | 3 hr | 0.5 hrs
5 | PECUNIABANK_05 | 1 | Testing the functionalites in postman |  | 2 hrs | 1hr

## Sumanth
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK:001 | 1 | Entity Class Design |  | 2020-08-03 | 2 hrs | 1 hr | Completed
|  | 2 | Use case diagram |  | 2020-08-03 | 1hr | 0.5 hr | Completed
|  | 3 | Sequence Diagram |  | 2020-08-03 | 1hr | 0.5hr | Completed
|  | 4 | Class Layer diagram |  | 2020-08-04 | 2 hrs | 1 hr | Completed
|  | 5 | Class Diagram |  | 2020-08-04 | 2 hrs |  | Completed
|  | 6 | TestCaseTemplate |  | 2020-08-03 | 2 hrs | 1hr | Completed | 2hrs
2 | PECUNIABANK:002 | 1 | Creating a Spring boot starter project |  | 2020-08-04 | 1 hr | 0.5 hrs | Completed
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 2020-08-04 | 1 hrs | 0,5 hrs | Completed
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 2020-08-05 | 1 hrs | 0,5 hrs | Completed
3 | PECUNIABANK:005 | 1 | Loan Request | DAO | 2020-08-05 | 3 hrs | 1.5 hrs | Completed
|  |  |  | SERVICE | 2020-08-06 | 3 hrs | 1.5 hrs | Completed
|  |  |  | CONTROLLER | 2020-08-06 | 3 hrs | 1.5 hrs | Completed
|  | 2 | Loan Disbursal | DAO | 2020-08-06 | 3 hrs | 1.5 hrs | Completed
|  |  |  | SERVICE | 2020-08-07 | 3 hrs | 1.5 hrs | Completed
|  |  |  | CONTROLLER | 2020-08-07 | 3 hrs | 1.5 hrs | Completed
4 | PECUNIABANK:007 | 1 | Populating the test data in database |  | 2020-08-10 | 3 hrs | 1 hr | Completed
5 | PECUNIABANK:008 | 1 | Testing the functionalites in postman | DAO, SERVICE, CONTROLLER | 2020-08-10 | 2hrs | 1hr | Completed
Completed